## java-scrum-shenanigan
Java Scrum Shenaniganery
Milestone 1
Name | Subitems | Person | Status | Est. Hours | Date
Word Doc of Domain/Products |  | Max Weber | Done | 2 | 2021-01-17
Design Report | Cover Page, Scrum Stuff, Design Documentation | Max Weber, Kayla Currier | Done | 2 | 2021-01-17
Subitems | Name | Owner | Status | Date
| Cover Page | Max Weber, Kayla Currier | Done
| Scrum Stuff | Max Weber, Kayla Currier | Done
| Design Documentation | Max Weber, Kayla Currier | Done
|  |  |  | 4 | 2021-01-17
Milestone 2 Sprint 1
Name | Subitems | Person | Status | Est. Hours | Date
Main Application Page(Home page) |  | Max Weber, Kayla Currier | Done | 2 | 2021-02-14
User Class |  | Max Weber | Done | 0.5 | 2021-02-14
User Model |  | Max Weber, Kayla Currier | Done | 1 | 2021-02-14
User Controller |  | Max Weber, Kayla Currier | Done | 1 | 2021-02-14
|  |  |  | 4.5 | 2021-02-14
Milestone 2 Sprint 2
Name | Subitems | Person | Status | Est. Hours | Date
User Database? |  | Max Weber | Done | 0.5 | 2021-02-14
Login |  | Kayla Currier | Done | 2 | 2021-02-14
Registration |  | Kayla Currier, Max Weber | Done | 2 | 2021-02-14
Design Report |  | Max Weber, Kayla Currier | Done | 1 | 2021-02-14
|  |  |  | 5.5 | 2021-02-14
Milestone 3 Sprint 1
Name | Subitems | Person | Status | Est. Hours | Date
EJB Main Application Refactoring |  | Max Weber, Kayla Currier | Done | 2 | 2021-03-07
EJB Login Page Refactoring |  | Max Weber, Kayla Currier | Done | 2 | 2021-03-07
EJB Registration Page Refactoring |  | Max Weber, Kayla Currier | Done | 2 | 2021-03-07
|  |  |  | 6 | 2021-03-07
Milestone 3 Sprint 2
Name | Subitems | Person | Status | Est. Hours | Date
Product Creation Model | Product Class, Product Database, Product Database Service, Product Business Service |  | Done | 3 | 2021-03-07
Subitems | Name | Owner | Status | Date
| Product Class | Max Weber
| Product Database | Kayla Currier
| Product Database Service | Max Weber, Kayla Currier
| Product Business Service | Max Weber, Kayla Currier
Design Report |  | Max Weber, Kayla Currier | Done | 1 | 2021-03-07
|  |  |  | 4 | 2021-03-07
Milestone 4 Sprint 1
Name | Subitems | Person | Status | Est. Hours | Date
Report/Display Products |  | Max Weber, Kayla Currier |  | 4
4
Milestone 4 Sprint 2
Name | Subitems | Person | Status | Est. Hours | Date
Update/Delete Products |  | Max Weber, Kayla Currier |  | 4
Design Report |  | Max Weber, Kayla Currier |  | 1
5
Milestone 5 Sprint 1
Name | Subitems | Person | Status | Est. Hours | Date
REST API Module(start) |  | Max Weber, Kayla Currier |  | 6
6
Milestone 5 Sprint 2
Name | Subitems | Person | Status | Est. Hours | Date
REST API Module(finish) |  | Max Weber, Kayla Currier |  | 6
Design Report |  | Max Weber, Kayla Currier |  | 1
7
Milestone 6 Sprint 1
Name | Subitems | Person | Status | Est. Hours | Date
Login Module Refactoring |  | Max Weber, Kayla Currier |  | 4
4
Milestone 6 Sprint 2
Name | Subitems | Person | Status | Est. Hours | Date
Java Doc |  | Max Weber, Kayla Currier |  | 0.5
Additional refactoring |  | Max Weber, Kayla Currier |  | 6
Design Report |  | Max Weber, Kayla Currier |  | 1
7.5